## Slide 1: Balanced scorecard slide 3
NORTH TOPSAIL BEACH FIRE STATION
October 18, 2023 – IFB Issued
October 24, 2023 – Specifications made available.
October 31, 2023 – Receive Audit and send to LGC.
October 31, 2023 – Mandatory Pre-Bid meeting held.
November 1, 2023 – Board of Aldermen to consider/approve Resolution with broad authorization ($8Million). The original estimate was $6-$7 million. I used $8 million, so we do not have to start the process over with the LGC.
November 1, 2023 – Board of Aldermen authorizes Public Hearing for December 6, 2023.
November 7, 2023 – 2pm is the final day and cut off time for questions from bidders.
November 14, 2023 – Final Addendums to be issued.
November 21, 2023 – Bids Due with public bid opening at 2pm. Six bids received. The bids ranged from $6,102,689 to $6,456,000
November 21-November 29, 2023 – Review of bids
November 22, 2023 – RFP finalized to solicit institutions for an Installment Financing Contract
November 29, 2023 – Bid Review completed with full recommendation for Board of Aldermen packet.
December 5, 2023 – Application submitted to LGC
December 6, 2023 – Public Hearing and consideration by Board of Aldermen to approve construction contract pending LGC approval.
December 13, 2023 – RFP responses due for the Installment Financing Contract
January 3, 2024 - Approval of the actual financing documents and selected bank.
January 9, 2024 – NC Local Government Commission Meeting – Receive approval/denial.
January 15-17, 2024 – Anticipated closing.
ORIGINAL TIMELINE PROVIDED:

## Slide 2: Balanced scorecard slide 3
NORTH TOPSAIL BEACH FIRE STATION
December 5 Submit LGC application
December 6 Town holds public hearing; accepts construction contract
December 13 RFP Responses Due
January 3 Town adopts Approving Resolution
January 9 LGC Meeting – Receive Approval/Denial
January 15-17 Closing
TIMELINE UPDATE:
 | Principal | Interest | Total
 | $ - | $ - | $ -
Year 1 | $ - | $ 135,375 | $ 135,375
Year 2 | $ 375,000 | $ 270,750 | $ 645,750
Year 3 | $ 375,000 | $ 252,000 | $ 627,000
Year 4 | $ 375,000 | $ 233,250 | $ 608,250
Year 5 | $ 375,000 | $ 214,500 | $ 589,500
Year 6 | $ 375,000 | $ 195,750 | $ 570,750
Year 7 | $ 375,000 | $ 177,000 | $ 552,000
Year 8 | $ 375,000 | $ 158,250 | $ 533,250
Year 9 | $ 375,000 | $ 139,500 | $ 514,500
Year 10 | $ 375,000 | $ 120,750 | $ 495,750
Year 11 | $ 375,000 | $ 102,000 | $ 477,000
Year 12 | $ 370,000 | $ 83,250 | $ 453,250
Year 13 | $ 370,000 | $ 64,750 | $ 434,750
Year 14 | $ 370,000 | $ 46,250 | $ 416,250
Year 15 | $ 370,000 | $ 27,750 | $ 397,750
Year 16 | $ 370,000 | $ 9,250 | $ 379,250
 | $ 5,600,000 | $ 2,230,375 | $ 7,830,375
SAMPLE AMORTIZATION SCHEDULE:
Total Project Amount: $5,600,000
Term: 15 Years
Interest Rate: 5%